## Slide 1: Convention Planning process revision proposal – again!
OCTA 2018 Spring Meeting

## Slide 2: Problems with current process
Too much work for small chapters
Limited expertise in chapters
Chapters must relearn every time they host
Side-Effects
  No increase in membership as a result of convention
  Often a loss of key members due to burn out
  Often a recovery period of several years for members
Nobody joins OCTA to plan a convention

## Slide 3: New process Key features
National to do tasks which are common and recurring
Chapters to do tasks specific to the location and chapter
Some tasks are shared between National and chapters
Share information between National and chapters
Develop and utilize lists and templates

## Slide 4: Benefits of change
Promotes cooperation and coordination between National and chapters
Utilizes previous knowledge and expertise for common tasks to promote consistency and ease of planning
Utilizes templates and information sharing to make recurring tasks easier
Promotes refinement and improvement of most areas over time by noting performance, good ideas, and sharing information

## Slide 5: templates
Category | Content
Communications | Media communications
Exhibitors & Sales Rooms | Contacting authors, publishers, and book sellers
Finances | Financial planning and reporting
Publications | Registration booklet Convention booklet Tour guide booklet
Registration | Registration workbook Attendee name badge
Sponsors | Letter requesting sponsorship

## Slide 6: Contact lists
Category | Content
Communications | Newspapers, media, federal, state, local entities
Entertainment | Dancers, musicians, performers, reenactors, etc.
Exhibitors & Sales Rooms | Authors, publishers, book sellers
Facilities | Available facilities which have been considered and used
Programs & Speakers | Available speakers and their presentations
Sponsors | Previous and potential sponsors
Transportation | Bus companies which have been considered and used
National maintains list and shares with chapter during planning
Chapter identifies additional entries and returns to national
National contacts entries
Lists may be email distribution lists

## Slide 7: other lists
Category | Content
Auction & Raffle | Sales information for future convention planning
Lessons Learned | Ideas and techniques which worked well and did not work well
Merchandise Sales | Sales information for future convention planning
Volunteers | Tasks frequently done by volunteers Sources of volunteers

## Slide 8: responsibilties
Task Category | Primary Responsibility
Auction & Raffle Merchandise Sales Tours Volunteers | Chapter
Communications Exhibitors & Sales Rooms Facilities Meals & Drinks Registration Risk Management Transportation (buses) | National
Entertainment Finances Programs & Speakers Publications Sponsors | Shared Between National and Chapter

## Slide 9: Task summary
Group | Tasks
Chapter | Obtain and sell auction and raffle items Obtain and sell convention related merchandise Develop publications and tour books based on templates Define tours Solicit volunteers Assist with determining entertainment, program & speakers Coordinate finances Solicit sponsors
National | Send all communications to media Arrange for exhibitors and sales rooms Arrange for facilities, hotels, meals, and drinks Coordinate publications and tour books Handle registration, risk management, and transportation Assist with determining entertainment, program & speakers Coordinate finances Solicit sponsors

## Slide 10: Next steps
Get consensus and support from National Officers and Board Of Directors
Determine who serves as “National” role
Develop templates
Develop list forms
Determine when to begin using the process